## Sheet1
Sprint 1 Backlog |  | Status | Who did what? What is done? What needs to be done?
Code Refactor
| Validate HTML & CSS | Done
Album search page
| Search form | Done
| Mock data | Done | Nick - 7 albums created. Working on 3 more
Album search result page
| Populate data |  | Nick/Bobby - 7 added. Will add the rest whenever they get done.
| Form validation | We got it to work. Check with prof to see if anything else may be needed? | Bobby/Nick - Added empty statements into results.php. Double check to see if this is all that's required.
| Data sanitization | Pretty much done | All - Make sure info is good. Function in the notes?
| Database query | Done. Search by title and artist is fine | Nick/Josh Bobby - Query works so far. Have to change the code to search by certain parameters rather than return the whole album table
| Page layout (table) | Done. What we have is fine | Bobby - Table created for results. Taken from lab 3
| Page layout if form invalid | Done | Bobby - message created for an empty query
Survey info into database
| Form validation | We got it to work. Check with prof to see if anything else may be needed? | All - Need to do with PHP. Use isset/notset
| Data sanitization | Pretty much done | All - Make sure info is good. Function in the notes?
| Database insert statement | Not Done | Josh - Insert into SQL
Clean up code!!! |  | Do at the end | Do at the end
Validate all pages |  | Do at the end | Do at the end